**12-Week PMO-AI Platform Launch Strategy**

This plan assumes your technical infrastructure works as designed. If discovery or scoring systems underperform, your 3 hours will shift to fixing automation rather than content creation, which breaks the model.

- Strategic direction adjustments

- Community relationship building

- Blog post topics and framing

- Weekly curation decisions (override automated selections when needed)

**Human Judgment Critical For:**

- MCP servers must process content efficiently

- Database must handle volume without issues

- Scoring system must accurately identify quality

- Discovery system must run reliably daily

**Automation Dependencies:**

5. Measure ruthlessly – If something doesn't drive subscribers or authority, stop doing it

4. Write strategically – Blog posts are thought leadership, not summaries

3. Engage authentically – Your LinkedIn time is relationship building, not broadcasting

2. Quality over volume – Let database scores guide curation

1. Stick to 3 hours weekly – Automation must handle everything else

**Don't Break These Rules:**

**Critical Success Factors**

- Sustainable system for long-term operation

- 3 hours weekly time investment maintained

- 90%+ automation of content pipeline

**Efficiency:**

- Consulting lead generation started

- Speaking inquiry or two

- 2-3 partnership opportunities

- 3-5 subscriber testimonials

**Authority:**

- 100+ LinkedIn posts

- 12 in-depth blog posts published

- 240+ original analysis pieces created

- 600+ discovered articles curated

**Content:**

- 50+ engaged community members

- 2,000+ LinkedIn connections

- 500+ newsletter subscribers

**Audience:**

**Success Metrics by Week 12**

- Performance optimization (data-driven adjustments)

- Community engagement (relationship building)

- Strategic content creation (blog posts)

- Quality curation oversight (minimal intervention)

**Your 3 Hours Focus:**

- Analytics compilation

- LinkedIn post publishing

- Email sequence triggers

- Newsletter data extraction from database

**Weekly Automated:**

- Social media post scheduling

- Track 2/3 content generation (4 pieces)

- Top 10 daily selections saved

- AI scoring and database storage

- Discovery system runs (150-200 articles)

**Daily Automated (Zero Weekly Time):**

**Automation Stack (Set & Forget)**

- Growth Target: 550+ subscribers

- Plan next quarter strategy (15 min)

- Blog: "Building PMO-AI Intelligence in Public" (45 min)

- Special newsletter: Quarter 1 insights compilation (60 min)

**Friday (2 hours):**

- Thank community

- LinkedIn: "12 Weeks - What We Learned"

**Wednesday (30 min):**

- Success analysis

- Final metrics review

**Monday (30 min):**

**Week 12: Launch Retrospective**

- Growth Target: 500 subscribers

- Set up cross-promotion automation (15 min)

- Guest blog post for partner platform (75 min)

- Newsletter (30 min)

**Friday (2 hours):**

- Guest post outreach

- LinkedIn: Cross-promote with complementary newsletter

**Wednesday (30 min):**

- Identify potential collaboration partners

- Curation review

**Monday (30 min):**

**Week 11: Strategic Partnerships**

- Growth Target: 450 subscribers

- Plan subscriber survey (15 min)

- Blog: "Reader Questions on PMO-AI" compilation (60 min)

- Newsletter addressing community questions (45 min)

**Friday (2 hours):**

- Respond to all comments

- LinkedIn: Host mini-discussion thread

**Wednesday (30 min):**

- Identify subscriber questions/themes

- Curation review

**Monday (30 min):**

**Week 10: Community Building**

- Growth Target: 400 subscribers

- Outreach to industry publications (15 min)

- Opinion piece blog: "Why Most PMOs Are Approaching AI Wrong" (75 min)

- Newsletter (30 min)

**Friday (2 hours):**

- Drive discussion in comments

- LinkedIn: Post strong opinion on AI-PMO trend

**Wednesday (30 min):**

- Identify contrarian insights

- Curation focusing on controversial/bold takes

**Monday (30 min):**

**Week 9: Thought Leadership Push**

**Phase 3: Authority Building (Weeks 9-12)**

- Growth Target: 350 subscribers

- Update automation based on learnings (15 min)

- Strategic planning blog post (60 min)

- Newsletter with best-of compilation (45 min)

**Friday (2 hours):**

- Engagement with community

- LinkedIn: Share "8 Weeks of Insights" post

**Wednesday (30 min):**

- Identify top-performing content types

- Comprehensive metrics review

**Monday (30 min):**

**Week 8: Mid-Point Assessment**

- Growth Target: 300 subscribers

- A/B test newsletter subject lines (15 min)

- Blog: Case study from Track 2 implementation (75 min)

- Newsletter (30 min)

**Friday (2 hours):**

- Test new content formats

- LinkedIn engagement

**Wednesday (30 min):**

- Adjust scoring thresholds if needed

- Review automation performance

**Monday (30 min):**

**Week 7: Automation Optimization**

- Growth Target: 250 subscribers

- Schedule posts featuring interview (15 min)

- Interview-style blog featuring PMO leader's AI perspective (75 min)

- Newsletter (30 min)

**Friday (2 hours):**

- Build relationship with key voices

- LinkedIn: Tag influencers in relevant content

**Wednesday (30 min):**

- Identify 3 PMO influencers to feature

- Curation review

**Monday (30 min):**

**Week 6: Guest Engagement**

- Growth Target: 200 subscribers

- Set up automated email sequence (30 min)

- Create "10 AI Tools for PMOs" PDF from database (60 min)

- Newsletter (30 min)

**Friday (2 hours):**

- Share in PMO groups

- LinkedIn: Announce lead magnet

**Wednesday (30 min):**

- Select 10 best Track 3 pieces for lead magnet

- Curation review

**Monday (30 min):**

**Week 5: Lead Magnet Launch**

**Phase 2: Growth (Weeks 5-8)**

- Growth Target: 150 subscribers

- Add testimonials to website (15 min)

- Blog: "Month 1 Insights - What We Learned" (60 min)

- Newsletter with testimonial feature (45 min)

**Friday (2 hours):**

- Engage with PMO influencers

- LinkedIn: Share subscriber testimonial

**Wednesday (30 min):**

- Email 5 engaged subscribers for feedback

- Curation review

**Monday (30 min):**

**Focus:** Capture early testimonials

**Week 4: Social Proof**

- Growth Target: 100 subscribers

- Update website meta descriptions (15 min)

- Blog post with SEO optimization (75 min)

- Newsletter (30 min)

**Friday (2 hours):**

- Share blog post in relevant groups

- LinkedIn engagement

**Wednesday (30 min):**

- Tag best pieces with SEO keywords for blog

- Same curation process

**Monday (30 min):**

**Focus:** Optimize content for search

**Week 3: SEO Foundation**

- Growth Target: 75 subscribers

- Schedule 3 LinkedIn posts for next week (15 min)

- Blog post: Expand selected Track 2/3 into 1500 words (75 min)

- Newsletter compilation (30 min)

**Friday (2 hours):**

- Cross-post to relevant LinkedIn groups

- Comment on 3-5 relevant PMO posts

- LinkedIn: Share Track 2 insight with engagement question

**Wednesday (30 min):**

- Identify 1 Track 2/3 piece for blog expansion

- Same curation review process

**Monday (30 min):**

**Focus:** Establish consistent publishing cadence

**Week 2: Content Rhythm**

- Growth Target: 50 subscribers

- Review week's metrics (15 min)

- Write 1 LinkedIn post previewing newsletter (15 min)

- Send newsletter to initial list

- Add personal commentary to top 3 picks (30 min)

- Edit newsletter intro (15 min)

- Newsletter auto-generated from database

**Friday (2 hours):**

- Respond to any comments/questions

- Engage with PMO community posts

- Share 2-3 best Track 3 insights on LinkedIn

**Wednesday (30 min):**

- Approve automated selections or manual override

- Quick scan of 20 created Track 2/3 pieces

- Verify top 10 selections look good

- Review week's discovered content (50 articles in database)

**Monday (30 min):**

**Week 1: Soft Launch**

**Phase 1: Foundation (Weeks 1-4)**

- Blog post outline structures

- LinkedIn post templates

- Track 2/3 brief generation prompts

- Newsletter template (auto-populate from database)

**Content Templates**

- LinkedIn scheduler configured

- Email platform setup with automation sequences

- MCP servers configured for content processing

- Database storing scored articles (automated)

- Discovery system running daily (automated)

**Technical Infrastructure**

**Pre-Launch Setup (Week 0)**

- Friday (2 hours): Newsletter compilation, blog writing, strategic review

- Wednesday (30 min): LinkedIn engagement & content distribution

- Monday (30 min): Weekly quality check & curation decisions

**Total Weekly Time Budget: 3 hours**

**Core Principle: Automate Everything, Curate Strategically**

Solo Operator | 3 Hours Weekly | Maximum Automation